**Minutes 16-02-2023 Two-weekly CADx meeting**

*Present: Anna Koch (AK), Terese Hellström (TH), Yunus Emre (YE)*, Sven Bierenbroodspot (SB) and Joost Nederend (JN)

*Absent: Janneke Hoogstad (JH), Tamar Gootzen (TG), Remko Bosgraaf (RB), Eveline Dekker, Jurgen Piek (JP), Caroline Muntinga (CM) Fons van der Sommen (FS), Tim Broers (TB) and Marion Welten (MW)*

Discussed:

* Actionlist: 02-02-2023
* Overview AK made 🡪 will be send to everybody by email
* SB will join the project until June 2023
* YE stays until end of March 2023 🡪 will give a presentation on his findings then  
  🡪 YE is currently not working on transformers
* CZE and TUE did not find a suitable master student yet to continue the project\
* Hanarth foundation 🡪 JN will apply with another preproposal as well on peritoneal metastasis  
  🡪 He agrees upon his name been put on the preproposal on AI and ovarian cancer

Actionlist 16-02-2023:

|  |  |  |  |
| --- | --- | --- | --- |
| **Whom** | **What** | **Date** | **Finished** |
| AK | NKI scans: will asks for 3mm scans first and later other ST scans from HE4 cohort | 03-02-2023  16-02-2023 | Received on TUe link the scans |
| AK + students | Will make a planning the annotations and data entry |  |  |
| AK + TG | Review | 16-02-2023 | Online |
| RB | **Awaiting  presentation on AI and benign ovarian tumor** |  |  |
| AK | Will arrange access for ED/IS for starting the annotations when her internship starts in March 2023 | 13-02-2023  16-02-2023 |  |
| AK + FvS + JP + JN + LE | Plan a reallife meeting to discuss the further progress of this project in the furture and write a funding proposal  Upcoming grand proposals are in March already |  |  |
| AK | Will make an overview of avaible data and what has been done so far by different student from CZE and TUe, also as a work-up for possible grand proposal | 16-02-2023 |  |
| YE | Will give a presentation on his final findings |  |  |
| AK | Will send review link to those whom did not received it |  |  |
| AK | Will Hanarth preproposal to JP, FS and JN for corrections |  |  |
| TH | Will check if she can forward the uploaded scans from the NKI to shared server, now TB is on holiday |  |  |
| AK | Will send powerpoint overview with the scans to those whom did not attend |  |  |