## Sheet1
| TU/e planning | Time allocation | Project phase | Deadlines |  | Project phases
[hrs/week]
2023-02-06 | start q3 | 5 | Phase 1 |  |  | Phase 1 | Project orientation, liturature research, installing and familiarize with tools.
2023-02-13 |  | 17 |  |  |  | Phase 2 | Replication of previous work
2023-02-20 | Carnival break |  |  | First planning deadline |  | Phase 3 | Discover different ideas
2023-02-27 |  | 17 |  |  |  | Phase 4 | Gather results
2023-03-06 |  | 17 |  |  |  | Phase 5 | document findings in paper + presentation
2023-03-13 |  | 17 |  | Draft introduction
2023-03-20 |  | 0 | Phase 2
2023-03-27 |  | 5
2023-04-03 |  | 10
2023-04-10 | exam week |  | Phase 3
2023-04-17 | exam week | 20
2023-04-24 | start q4 | 20 |  | Midterm draft full report
2023-05-01 |  | 20 |  | Updated planning deadline | Intermediate paper deadline
2023-05-08 |  | 20 | Phase 4
2023-05-15 |  | 20
2023-05-22 |  | 20 | Phase 5
2023-05-29 |  | 20
2023-06-05 |  | 20
2023-06-12 |  | 17 |  | Final paper deadline | Reflection report deadline
2023-06-19 |  | 15 |  | Final presentations
2023-06-26 | exam week
2023-07-03 | exam week
10 ECTS | = 280 hrs | 280